## Sheet1
Features | % complete | % tested | time to completion
Make Ah+C5:F34ead Reminder for Events | 35% | 0% | 17 hours
Test system with single command | 100% | N/A | N/A
Deploy server with simple command | 0% | 0% | 6 hours
Change password while logged in | 50% | 0% | 1 hour
Request password if forgoten | 100% | 0% | Complete
Complete login process without having to login more than once | 100% | 80% | Complete
User can log in to use system | 100% | 100% | Complete
No duplicate registration for event | 70% | 0% | 5 hours
Assign event location without location conflict | 20% | 0% | 14 hours
Change location of every event simultaneously | 100% | 0% | Complete
Student can register to participate in events | 100% | 0% | Complete
Teacher can login to access class and student information | 85% | 0% | 2 hours
Create a new event as a sponsor | 100% | 0% | Complete
Teachers can create accounts | 100% | 50% | Complete
Team registration decreases capacity | 0% | 0% | 2 hours
Register in a single slot as a team | 0% | 0% | 2 hours
Sponsors can delete or modify events | 100% | 0% | Complete
Teachers can print a checkin list for students | 0% | 0% | 3 hours
You can retrieve event details without having to log in | 100% | 50% | Complete
You can print event summary page | 50% | 0% | 3 hours
You can access the events summary page | 100% | 20% | Complete
As a team lead you can modifty the teams registration details | 0% | 0% | 2 hours
As a student you can create a team | 0% | 0% | 2 hours
As a student you can print your teams schedule | 0% | 0% | 3 hours
Display team schedule | 0% | 0% | 30 minutes
You can print a list of register team members | 0% | 0% | 1 hour
You can access team info | 0% | 0% | 30 minutes
Teacher can view summary of class and each student status | 50% | 0% | 2 hours
Teacher can print schedule of individual students | 25% | 0% | 2 hours
Display student schedules as a whole class | 50% | 0% | 2 hours
Display schedules of each registered student | 20% | 0% | 30 minutes
Teacher can print a list of registered student | 50% | 0% | 1 hour
A team can have a minimum of two and a max of four | 0% | 0% | 1 hour
Teams can register for events | 0% | 0% | 6 hours
Sponsors can register to create and edit events | 100% | 50% | Complete
Over capacity of events have a wait list | 0% | 0% | 17 hours
Teacher can add students | 100% | 50% | Complete
Teacher can register for events | 0% | 0% | 3 hours
Make ahead reminders one week ahead of prior to the activity | 0% | 0% | 17 hours